## Sheet1
Patch tab to use | CHG_start_date | CHG_end_date | PatchingGroup | Server | Description | Env | Owner/1st Contact | 2nd Contact | In-window Support Requirements | Co-ordination notes | Category
RH5 Patching steps | 2019-01-02 21:00 | 2019-03-02 05:00 | Dev_1 | CH3TR019845 | ` | Development | Dacob janiel | Chris poole | Aplication stop/Start:NONE(If yes , need two contacts) In-window(If yes, need two contacts) |  | Linux
RH5 Patching steps | 2019-01-02 21:00 | 2019-03-02 05:00 | Dev_1 | CH3PR016586 | Data relocation | Development | Devang joshi | Anil Menon | Aplication stop/Start:NONE(If yes , need two contacts) In-window(If yes, need two contacts) |  | Linux
RH5 Patching steps | 2019-01-02 21:00 | 2019-03-02 05:00 | Dev_1 | CH3BR015586 | Enterprise manager | Development | John Smith | Oracle AppDBa | Aplication stop/Start:NONE(If yes , need two contacts) In-window(If yes, need two contacts) |  | Linux
RH5 Patching steps | 2019-01-02 21:00 | 2019-03-02 05:00 | Dev_1 | CH3AR016586 | Enterprise manager12 | Development | Pull reddy | Gayathree | Aplication stop/Start:NONE(If yes , need two contacts) In-window(If yes, need two contacts) |  | Linux
RH5 Patching steps | 2019-01-05 21:00 | 2019-03-02 05:00 | Dev_5 | CH3DP020661 | Linux test server | Development | Russell house | Mark | Aplication stop/Start:NONE(If yes , need two contacts) In-window(If yes, need two contacts) |  | Linux
RH5 Patching steps | 2019-01-05 21:00 | 2019-03-02 05:00 | Dev_5 | CH3CP123654 | Oraccle app | Development | Tim | Lisa shileds | Aplication stop/Start:NONE(If yes , need two contacts) In-window(If yes, need two contacts) |  | Linux
RH5 Patching steps | 2019-01-05 21:00 | 2019-03-02 05:00 | Dev_5 | CH3UP136591 | Yum repo | Development | Tom nicarsti | Steve stephen | Aplication stop/Start:NONE(If yes , need two contacts) In-window(If yes, need two contacts) |  | Linux
RH5 Patching steps | 2019-01-02 21:00 | 2019-03-02 05:00 | PROD_3 | PS2PR024569 | EBS | Production | Dan Power | Balaji Kopala | Aplication stop/Start:NONE(If yes , need two contacts) In-window(If yes, need two contacts) |  | Linux
RH5 Patching steps | 2019-01-02 21:00 | 2019-03-02 05:00 | PROD_3 | PS2PR023689 | Core capalities | Production | David John | Midrange unix services | Aplication stop/Start:NONE(If yes , need two contacts) In-window(If yes, need two contacts) |  | Linux
CentOS 7 Paching steps | 2019-01-02 21:00 | 2019-03-02 05:00 | PROD_3 | Blmar029533 | Blm -scaengine | Production | EAM Core capablities@expresscript.com | Paul Genteli | Aplication stop/Start:NONE(If yes , need two contacts) In-window(If yes, need two contacts) |  | Linux
RH5 Patching steps | 2019-01-02 21:00 | 2019-03-02 05:00 | PROD_4 | PS2PR023569 | Splunk | Production | Rahil Rajan | Aziz | Aplication stop/Start:NONE(If yes , need two contacts) In-window(If yes, need two contacts) |  | Linux
CentOS 7 Paching steps | 2019-01-02 21:00 | 2019-03-02 05:00 | PROD_4 | Blmar029534 | Blm -scaeng | Production | Srikanth | JimMackuser | Aplication stop/Start:NONE(If yes , need two contacts) In-window(If yes, need two contacts) |  | Linux
RH5 Patching steps | 2019-01-02 21:00 | 2019-03-02 05:00 | QA_UAT_1 | CH3QR016633 | Mq server | QA | Randeep toor | Middleaware support | Aplication stop/Start:NONE(If yes , need two contacts) In-window(If yes, need two contacts) |  | Linux
RH5 Patching steps | 2019-01-02 21:00 | 2019-03-02 05:00 | QA_UAT_1 | CH3QR016635 | Client valication benefits | QA | Rupa Joshi | David de jesus | Aplication stop/Start:NONE(If yes , need two contacts) In-window(If yes, need two contacts) |  | Linux
RH5 Patching steps | 2019-01-02 21:00 | 2019-03-02 05:00 | QA_UAT_1 | CH3QR016635 | Client valication benefits | QA | Rupa Joshi | David de jesus | Aplication stop/Start:NONE(If yes , need two contacts) In-window(If yes, need two contacts) |  | Linux